## Sforce - NetSuite Mapping
Context : Vendor /Publisher Detail
Netsuite Object Name | vendor
Salesforce Object Name | Account(Record Type - Publisher)
NetSuite UI Display Name | NetSuite API Name (for reference only) | Salesforce UI Display Name | Salesforce API Name | Data Type | Length | Comments
External ID | custitem_sni_external_id | Netsuite Vendor Id | MBDSFA_Publisher_Id__c | Text (External ID) | 255
Company Name | companyname | Name | Name | Name | 120
Primary Subsidiary | subsidiary |  |  |  |  | Defaulted to "SmartNews International Inc." (Id:4)
Email Address for Payment Notification | custentity_2663_email_address_notif |  | SFDC Table -> Contract and filter Depart/Title == 'payment recipent' and Contarct.AccountId = Account.Id |  |  | Need to verify with Aura about where these emails seems to be stored in Salesforce | Field is not created or no visibility | Sridhar Syagamreddy
Publisher Item Name / Number (New List) | custentity_publisher_item_name_number_n |  |  |  |  | This needs to be update from Pricing Tier by using Salesforce ID | Field is not created or no visibility | Sridhar Syagamreddy
Salesforce Id | custentity_salesforce_id | Id | Id | Text | 18 |  | Field is not created or no visibility | Sridhar Syagamreddy
Category | category | Payment Category | MBDSFA_Payment_Category__c | Picklist |  | id for 5: Monthly Publishers 6: Quarterly Publishers | In case of null value what should be defaulted, also as it is picklist please provide internal id or lookup logic | Sridhar Syagamreddy
Email | email | Company Email | MBDSFA_Email__c | Email
Web Address | url | Website | Website | URL | 255
Site ID | custentity_site_id | Site ID |  | Text
Default Payables Account | payablesaccount |  |  |  |  | Set Default account as 201300 Accounts payable (id:530)
Inactive | isinactive | if delete = true make |  |  |  |  | Sunil Manth Please provide the corresponding mapping. | Sunil- We do not have such field in salesforce
Primary Currency | currency |  |  |  |  | Defaulted to "USD" from Subsidiary (id:2)
Country | addressbookAddress.country | Shipping Country | ShippingCountry | Text |  |  | Sridhar Syagamreddy Country field is not available, please check. Also provide the logic to get internal id of the country.
Phone | addrphone | Phone | Phone | Phone
Address1 | addr1 | Shipping Street | ShippingStreet | Text | 255
Address2 | addr2 |  |  |  | 255
City | city | Shipping City | ShippingCity | Text | 255
State | dropdownstate | Shipping State/Province | ShippingState | Text |  |  | Sridhar Syagamreddy Please check the proper name or it's visibility. Also share the picklist mapping logic.
Zip | zip | Shipping Zip/Postal Code | ShippingPostalCode | Text | 255
Addressee | addressee | Name | Name

## Cutover Tasks
Vendor Integration Production Deployment Checklist
S.No | Task Description | Status | Owner | Target Completion Date | Actual Completion Date
1 | Take the backup of all the Vendors (including Subsidiaries) and Items in Production | Pending | Sridhar | 2023-08-31
2 | Move the field mapping based on the Mapping Document | Pending | Sridhar | 2023-09-01
2 | To assign the Custom Item Fields Permission to the Roles "SnapLogic_API_Role" and "SnapLogic_Nestsuite_ODBC" | Pending | Sridhar | 2023-09-01
3 | To assign "items" master data permission to the Roles "SnapLogic_API_ROle" and "SnapLogic_Nestsuite_ODBC" | Pending | Sridhar | 2023-09-01
4 | To Assign Custom Entity Fields to the Roles "SnapLogic_API_ROle" and "SnapLogic_Nestsuite_ODBC" | Pending | Sridhar | 2023-09-01
5 | To assign the Subsidiary permission to the Roles "SnapLogic_API_ROle" and "SnapLogic_Nestsuite_ODBC" | Pending | Sridhar | 2023-09-01
6 | Establish snaplogic pipeline for production instance | Completed | Supratim | 2023-09-01
7 | WSDL changes in NS account | Completed | Supratim | 2023-09-01
8 | Create Audit Trail Prod table for Vendor in Snowflake | Completed | Supratim | 2023-09-01
9 | Dry run and verify the data | Pending | Supratim / Sridhar | 2023-09-01
10 | Move the custom field "Payment Notification E-Mail Address {Holds API Values}" into Production | Pending | Sridhar | 2023-09-11
11 | Move the Script " Update Email Add for PYMT Notification" to prod to update Email Address for Payment Notification | Pending | Sridhar | 2023-09-11
12 | To configure auto generated number on Vendor with prefex as "temp-" | Pending | Sridhar | 2023-09-12

## Item Mapping
Context : Item Detail
Netsuite Object Name | item
Salesforce Object Name | pricing_tier__c
NetSuite UI Display Name | NetSuite API Name (for reference only) | Data Source | Field Name | Salesforce API Name | Data Type | Length |  | Comments
Item Name / Number | itemid | pricing_tier__c | MBDSFA_PUBLISHER_ITEM__C |  |  | 250
Publisher Category | custitem_dps_snc_item_category | [5 empty] | Review Publisher Category on the Form and remove if not require | Id for 5: Monthly Publishers 6: Quarterly Publishers
Expense Account | expenseaccount | Default Value (Account id: Value 589) | [5 empty] | By Default "501130 Cost of Sales: Cost of Sales: Cost of sales: Advertising (Cost)" (id:589)
Tax Schedule | taxschedule | Default Value (tax id: Value 2) | [5 empty] | By Deault " Non-Taxable" (id:2)
Subsidiary | subsidiary | Default Value (subsidiary Id : Value 1) | [5 empty] | By Deault " Primary Subsidiary" (id:1)
Include Children | includechildren | Default to 'True' | [5 empty] | By Default needs to set "True"
For Item deactivation it should be handled by Business Owner
Item --- Vendor --- Bank Details --- Pricing Tier

## Beyond Program Publisher URL Ma
Context | Beyond Program
Netsuite Object Name | Publisher URL(Publisher's URL (233))
Salesforce Object Name | Publisher Program (Publisher_Program__c)
NetSuite UI Display Name | NetSuite API Name (for reference only) | Salesforce UI Display Name | Salesforce API Name | Data Type | Object Level | Length | Comments
Vendor Name | custrecord_publisher_name_vendor |  |  |  | Publisher URL (Internal ID:233) |  | By using Salesforce Id we wil update/tag vendor Name (using Vendor Internal ID)
Publisher URL / Descriptions | custrecord_publisher_url | URL | URL__c | Text | Publisher URL
Publisher Program ID | custrecord_publisher_program_id | Publisher Program Name | Name | Text | Publisher URL
Beyond | custrecord_beyond |  |  | Yes/No (T/F) | Publisher URL |  | Beyond is "T" when the Calc Level is "Brand" and Publisher URL / Website should have a value
Pub Program Start Date | custrecord_beyond_start_date | Start Date | Start_Date__c | Text | Publisher URL
Pub-Prog Calc Level | custentity_pprog_calculation | Calc Level | Calc_Level__c |  | Vendor Level / Custom Tab |  | Values : Publisher (Internal Id:1) Brand (Internal Id: 2)
Beyond% | custentity_beyond_percentage | Bonus% | Bonus__c | Percentage Value | Vendor Level / Custom Tab
Minimum Guarantee (MG) | custentity_beyond_mg | MG | MG__c | Decimal Value | Vendor Level / Custom Tab
Pub-Prog Start Date | custentity_startdate | Start Date | Start_Date__c | Text | Vendor Level / Custom Tab
Inactive Publisher Program | custentity_inactive_publisher_program | Inactive |  | Yes/No (T/F) | Vendor Level / Custom Tab
Publisher Program ID | custentity_program_program_id | Publisher Program Name | Name | Text | Vendor Level / Custom Tab
If Program level is "Publisher", need to update the following fields | 1) PUB-PROG CALC LEVEL 2) Beyond% 3) Minimum Guarantee (MG) 4) Pub-Prog Start Date
If Program level is "Brand", need to update the following fields | 1) Vendor Name 2) Publisher URL / Website Name 3) Publisher Program ID 4) Beyond (Flag) to "True" 5) Pub-Prog Calc Level 6) Beyond% 7) Minimum Guarantee (MG) 8) Pub-Prog Start Date